## History work session
Create date | Task group 1 | Task group 2 | Task group 3 | Time accept task | Task detail | for | Dự kiến thời gian thực hiện | Start time | processing (%) | Status | Finish | Counter hour | Accident | add content | Note for fix
2024-04-10 | Xây dựng hệ thống System |  |  | 2024-04-10 16:02
2024-04-10 |  | Kiểm tra sysAction |  | 2024-04-10 16:02 | Kiểm tra chức năng CURD 1. Get danh sách aciton theo permisison | Nguyễn Khánh | 2024-04-10 | 2024-04-10 14:02 | 100% | Đã xong | 2024-04-10 16:02 | 0.083333
2024-04-10 |  | SysDropdownAction |  | 2024-04-10 16:02 | Xây dựng control CURD | Nguyễn Khánh | 2024-04-12 | 2024-04-10 14:02 | 0% | Đang xử lí |  | -45392.5847
2024-04-10 |  | StatusMessenger |  | 2024-04-10 16:02 | Trả về messenger theo ngôn ngữ | Nguyễn Khánh | 2024-04-12 | 2024-04-15 06:20 | 25% | Đang xử lí |  | -45397.2639 |  | 10/04/2024 2:02:00 AM: Đã cấu hình hàm GetMessageDescription | 10/04/2024 2:02:00 AM: GetMessageDescription truyền accont vào để có thể xác định ngôn ngữ của account đó
2024-04-10 |  |  | Language | 2024-04-10 16:02 | Tạo bảng | Nguyễn Khánh | 2024-04-12 | 2024-04-15 05:40 | 100% | Đã xong | 2024-04-15 06:20 | 0.027778 |  | 10/04/2024 2:02:00 AM: Chưa tạo migration 15/04/2024 6:20:00 AM: Đã tạo và connect DB
2024-04-10 |  |  | Account | 2024-04-10 16:02 | Thêm trường language | Nguyễn Khánh | 2024-04-12 | 2024-04-10 14:02 | 100% | Đã xong | 2024-04-10 16:02 | 0.083333 |  | 10/04/2024 2:02:00 AM: Chưa tạo migration 15/04/2024 6:20:00 AM: Đã tạo và connect DB
2024-04-10 | LogTimeDataUpdate |  |  |  | Tạo bảng lưu những cập nhật của người dùng. Cần có 1 quy ước chung cho điều này vì số lượng dòng là rất lớn vì vậy sẽ tạo log theo thời gian là 3 tháng. Cách đặt tên sẽ là LogTimeDataUpdate124 ý nghĩa là quý 1 năm 2024 | Nguyễn Khánh | 2024-04-12 |  | 0% | Lên kế hoạch CV |  | 0
2024-05-02 | Insert/ update sysMenu |  |  |  | When do insert or update sysMenu then auto find sysMenu parent of this after add to column idMenuParent in table sysMenu |  |  |  | 0% |  |  | 0
17/05/2024 | Task daily | [7 empty] | 0% |  |  | 0
|  | Add column in voucherForm |  |  | Add new column query in VoucherFormColumnModel and table in sql | Nguyễn Khánh |  |  | 0% |  |  | 0
|  | Create API run query |  |  | 1. Create common controler 2. Create API exec query in common controler and test | Nguyễn Khánh |  |  | 0% |  |  | 0
|  | Create table CommonCategory |  |  | Id groupID code name name1 name2 name3 | Nguyễn Khánh |  |  | 0% |  |  | 0
|  | Create UI Group and update voucher-form-component |  |  | 1. Config grop and voucherFormComponent 2. Get API Search group after filter data in group | -- |  |  | 0% |  |  | 0
17/05/2024 | AutoForm |  |  |  | Create selectBoxComponent 1. Normal 2. Auto get datasource when have value of groupID | Nguyễn Khánh |  |  | 0% |  |  | 0
17/05/2024 | Create selectBox component | [7 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
[9 empty] | 0% |  |  | 0
Formulas:
Counter hour = [Finish]-[Start time]

## Common
Trạng thái | Nhân sự
Lên kế hoạch CV | Nguyễn Khánh
Đang xử lí | --
Đã xong | --
Đã kiểm thử | --
Gặp vấn đề khi xử lí | --
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--

## DocumentManagement
column | description
code
module
tableName
isCompanyCode
description
isClose
codeLogTime | connect table logtime

## LogTime{CodeCompany}
column | description
id
time
actor
action
description